## QuarterlyPlan
Quarter | Milestones | Due Date
Q1 | Repo + Cloud Shell ready; local CI with Makefile runs
Q2 | GitHub Actions green on push; docs started
Q3 | Azure App Service created; Azure Pipelines deploys
Q4 | Demo video + polish README; stretch: alerts/monitoring

## WeeklyPlan
Week # | Start | End | Deliverables (examples) | Status | Notes
1 | 2025-08-15 | 2025-08-21 |  | Planned
2 | 2025-08-22 | 2025-08-28 |  | Planned
3 | 2025-08-29 | 2025-09-04 |  | Planned
4 | 2025-09-05 | 2025-09-11 |  | Planned
5 | 2025-09-12 | 2025-09-18 |  | Planned
6 | 2025-09-19 | 2025-09-25 |  | Planned

## Tasks&Estimates
Task | Category | Estimate (hrs) | Difficulty (1-5) | Status
Create GitHub repo | Planning/Setup | 0.5 | 1 | Planned
Open Azure Cloud Shell, generate SSH key, link to GitHub | Setup | 0.5 | 2 | Planned
Add Makefile, requirements.txt, hello.py, test_hello.py | Coding | 1 | 2 | Planned
Run make all in Cloud Shell (screenshot) | CI Local | 0.5 | 1 | Planned
Add GitHub Actions workflow (screenshot badge) | CI Remote | 1 | 2 | Planned
Create Azure App Service via az webapp up | Azure | 1 | 2 | Planned
Create Azure DevOps project + service connection | Azure Pipelines | 1 | 3 | Planned
Add azure-pipelines.yml and run pipeline (screenshot) | Azure Pipelines | 1 | 3 | Planned
Test prediction endpoint (screenshot + logs) | Testing | 0.5 | 2 | Planned
Finalize README + commands.sh + video | Docs | 1.5 | 2 | Planned