## Tasks&Estimates
Yearly Plan 2025
Quarterly Plan Q1
Project Name | udacity-azure-ci-cd |  | PM | Jana Alharbi | Start Date | January 06, 2025 | End Date
Week (Estimation of time) | Start | End | Sprint | Release # | Feature | Points (Estimation of points) | Status
Week 01 | January 06, 2025 | January 12, 2025 |  |  | Project Analysis | 5 | Done
Week 02 | January 13, 2025 | January 19, 2025 | Sprint 1 |  | Repo & Cloud Shell setup (SSH, clone) | 5 | Done
Week 03 | January 20, 2025 | January 26, 2025 |  |  | Makefile + requirements + hello/tests | 8 | Done
Week 04 | January 27, 2025 | February 02, 2025 | Sprint 2 | 1.10 | Run make all (fix lint & tests) | 5 | Done
Week 05 | February 03, 2025 | February 09, 2025 |  |  | GitHub Actions (CI) green badge | 5 | Done
Week 06 | February 10, 2025 | February 16, 2025 | Sprint 3 |  | Azure App Service RG + az webapp up | 8 | Done
Week 07 | February 17, 2025 | February 23, 2025 |  |  | Flask ML app + train/serialize model.joblib | 5 | Done
Week 08 | February 24, 2025 | March 02, 2025 | Sprint 4 | 1.20 | Azure Pipelines: service connection + YAML | 8 | Done
Week 09 | March 03, 2025 | March 09, 2025 |  |  | Fix pipeline (self-hosted agent & reqs) | 5 | Done
Week 10 | March 10, 2025 | March 16, 2025 | Sprint 5 |  | App settings + Gunicorn startup (health OK) | 5 | Done
Week 11 | March 17, 2025 | March 23, 2025 |  |  | Prediction test (/features, /predict) + logs | 5 | Done
Week 12 | March 24, 2025 | March 30, 2025 | Sprint 6 | 1.30 | Documentation: README + screenshots + video | 8 | Done
Week 13 | March 31, 2025 | April 06, 2025 |  |  | Buffer, polish & submission | 5 | Done
Top 3 Quarter Goals |  |  |  | Project Management Guidelines
Deploy ML API with CI/CD to Azure |  |  | Proposed Difficulty 1-3 | 3 |  | Demo last day of every sprint.
Automated tests & linting pass everywhere |  |  | Proposed Difficulty 1-3 | 2 |  | Bi-Weekly planning after demo
Clear documentation & demo video |  |  | Proposed Difficulty 1-3 | 1 |  | Consumer/Stakeholder Release every 4 weeks
Tickets represent a 4-hour ~ 3 day block of work

## Yearly_Plan
Quarter | Start Date | End Date | Milestone/KPI | Owner | Status | Notes
Q1 2025 | Jan 6, 2025 | Mar 30, 2025 | CI scaffold + GitHub Actions + local tests | Jana Alharbi | Done
Q2 2025 | Apr 7, 2025 | Jun 29, 2025 | Cloud resources + App Service provisioning | Jana Alharbi | Done
Q3 2025 | Jul 7, 2025 | Sep 28, 2025 | End-to-end CD with Azure Pipelines | Jana Alharbi | Done
Q4 2025 | Oct 6, 2025 | Dec 28, 2025 | Monitoring, logging, performance and docs | Jana Alharbi | Planned