## Yearly Plan
Quarter | Start Date | End Date | Milestones | Key Deliverables | Est. Points | Status
Q1 2025 | 2025-01-06 | 2025-03-30 | CI/CD to Azure; first ML API live | GitHub Actions CI; Azure Pipelines CD; App Service; /predict endpoint | 40 | Done
Q2 2025 | 2025-04-07 | 2025-06-29 | Model quality & testing improvements | Unit tests for model; retrain script; logging | 35 | Planned
Q3 2025 | 2025-07-07 | 2025-09-29 | Observability & automation | Alerts; dashboards; scheduled retraining | 30 | Planned
Q4 2025 | 2025-10-06 | 2025-12-29 | Hardening & docs | Security review; backup/DR; full runbook | 25 | Planned

## Quarterly Plan – Q1 (Original)
Week (Estimation of time) | Start Date | End Date | Sprint | Release # | Feature / Task | Category | Est. Hours | Difficulty (1-3) | Owner | Status | Notes
Week 01 | 2025-01-06 | 2025-01-12 | 1 | 0.1 | Understand rubric & plan (Trello + Excel) | PM | 5 | 1 | Jana | To Do
Week 02 | 2025-01-13 | 2025-01-19 | 1 | 0.1 | Repo + Cloud Shell setup | DevOps | 3 | 1 | Jana | To Do
Week 03 | 2025-01-20 | 2025-01-26 | 2 | 0.2 | Makefile + tests + lint | Dev | 4 | 2 | Jana | To Do
Week 04 | 2025-01-27 | 2025-02-02 | 2 | 0.2 | GitHub Actions CI (badge green) | CI | 4 | 2 | Jana | To Do
Week 05 | 2025-02-03 | 2025-02-09 | 3 | 0.3 | Azure App Service (az webapp up) | Cloud | 5 | 2 | Jana | To Do
Week 06 | 2025-02-10 | 2025-02-16 | 3 | 0.3 | Service connection + Azure Pipelines (CD) | CD | 6 | 3 | Jana | To Do
Week 07 | 2025-02-17 | 2025-02-23 | 4 | 0.4 | Train model + save model/model.joblib | ML | 4 | 2 | Jana | To Do
Week 08 | 2025-02-24 | 2025-03-02 | 4 | 1 | Deploy ML API + verify /predict | CD | 5 | 2 | Jana | To Do
Week 09 | 2025-03-03 | 2025-03-09 | 5 | 1 | README + video + screenshots | Docs | 6 | 1 | Jana | To Do

## Quarterly Plan – Q1 (Final)
Week (Estimation of time) | Start Date | End Date | Sprint | Release # | Feature / Task | Category | Est. Hours | Actual Hours | Difficulty (1-3) | Owner | Status | Notes
Week 01 | 2025-01-06 | 2025-01-12 | 1 | 0.1 | Understand rubric & plan (Trello + Excel) | PM | 5 | 5 | 1 | Jana | Done
Week 02 | 2025-01-13 | 2025-01-19 | 1 | 0.1 | Repo + Cloud Shell setup | DevOps | 3 | 3 | 1 | Jana | Done
Week 03 | 2025-01-20 | 2025-01-26 | 2 | 0.2 | Makefile + tests + lint | Dev | 4 | 4 | 2 | Jana | Done
Week 04 | 2025-01-27 | 2025-02-02 | 2 | 0.2 | GitHub Actions CI (badge green) | CI | 4 | 4 | 2 | Jana | Done
Week 05 | 2025-02-03 | 2025-02-09 | 3 | 0.3 | Azure App Service (az webapp up) | Cloud | 5 | 5 | 2 | Jana | Done
Week 06 | 2025-02-10 | 2025-02-16 | 3 | 0.3 | Service connection + Azure Pipelines (CD) | CD | 6 | 6 | 3 | Jana | Done
Week 07 | 2025-02-17 | 2025-02-23 | 4 | 0.4 | Train model + save model/model.joblib | ML | 4 | 4 | 2 | Jana | Done
Week 08 | 2025-02-24 | 2025-03-02 | 4 | 1 | Deploy ML API + verify /predict | CD | 5 | 5 | 2 | Jana | Done
Week 09 | 2025-03-03 | 2025-03-09 | 5 | 1 | README + video + screenshots | Docs | 6 | 6 | 1 | Jana | Done